**Safer Woking Partnership Priorities**

Note: The priorities below are listed alphabetically not in a priority order

|  |  |
| --- | --- |
| **Priority**  | **Detail** |
| 1 | **Antisocial behaviour (ASB)*** Identify and support repeat and vulnerable victims of ASB and tackle the anti-social behaviour of individuals and families through the CHaRMM process and the Family Support Programme (FSP)
* Identify and address hotspot locations of ASB, particularly repeat locations, reported and actioned as appropriate through the JAG process and, if involving Serious and Organised Crime (SOC), through the SOC JAG
* To safeguard public spaces through the removal of disorder by appropriate use of Dispersal Orders, PSPOs and other appropriate ASB legislation.
* Take steps to address key anti-social behaviours as identified through consultation.
 |
| 2 | **Crime*** Educating young people around dangers of carrying knives.
* Tackling domestic abuse is a key priority recognised county wide
	+ Raise awareness of domestic abuse, how to report it and how to get support
	+ Work with our local specialist domestic abuse service, Your Sanctuary, in the provision of support to survivors of domestic abuse living in our community
	+ Work with the Domestic Abuse Management Board to implement the Surrey Domestic Abuse Strategy and support local and county wide campaigns
* Promote partnership resilience and awareness of Serious and Organised Crime, including County Lines, Cuckooing, Child Exploitation (Criminal and Sexual), Modern Slavery, fraud and Organised Crime Groups through partnership and community/business training and joint responses to local problems, such as the Risk Management Meeting (RMM)
* Tackle and raise awareness of Hate Crime across the Borough and build up community confidence in reporting incidents
* Work with Partners to ensure that victims, where appropriate, receive a multi-agency approach to safeguarding
* Promotion of intelligence submissions from non-Police partners
 |
| 3 | **Drugs and Alcohol*** Support appropriate partnership work that will assist with the implementation of the Woking Health and Wellbeing Strategy and Action Plan
* Development and implementation of suitable activity to tackle issues of concern in the town centre, particularly around the night-time economy, which includes supporting the PSPO, town centre dispersal orders and Woking Street Angels
* Support the local implementation of the Surrey Substance Misuse Strategy
* Tackle local issues through local operations, including test purchasing and licencing reviews
* Partnership support to proactive Police led operations to tackle drug supply and exploitation of the vulnerable
* Treatment pathways - to support and monitor Woking offenders in accessing and engaging with the treatment pathway for drug and alcohol misuse
 |
| 4 | **Preventing violent extremism*** Work together on the implementation of relevant aspects of local agency Prevent plans
 |
| 5 | **Reducing reoffending*** To work in partnership in assessing, managing and implementing Court sentences for those convicted offenders who have the greatest impact on the community in Woking through MARAC (Multi Agency Risk Management for high-risk DA cases), IOM (Integrated Offender Management), MAPPA (Multi-Agency Public Protection Arrangements for violent and sexual offenders) and MATAC (Multi Agency Tasking and Coordination for DA perpetrators)
* To contribute to the assessment and action planning of offenders who present a detrimental impact upon the community in Woking via the CHaRMM process
* To continue to support the work of the Women's Support Centre Surrey
* To work with Surrey Family Support Service in successfully managing the transition of young adult offenders into the adult Probation system
* To support and monitor Woking offenders in accessing and engaging with the treatment pathway for drug and alcohol misuse
* Community Payback - to empower people on probation to complete their community payback hours whilst learning new skills and improving their employment prospects and developing confidence in those harder to reach people.
* To work with community partners to deliver the order of the Court through projects that benefit the local community.
 |

**Action Plan for 2023/24**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Area** | **Delivery** | **Success measures** | **Target** | **Monitor/leads** |
| **Anti-social behaviour** | PSPO monitored through agreed enforcement strategy, reporting at JAG | Accurate recording of breachesReferrals made from identified repeat offendersFPN or Court outcomes | Throughout duration of action plan | Oli Walker |
| Partnership ASB locations and themes reporting at JAG | Number of relevant referrals received or number of referrals completed | JAG meetings (every 6-7 weeks)SOC JAG meetings (every 6-7 weeks) | Camilla EdmistonNell Rodriquez |
| Partnership ASB week w/c 3rd July 2023 | Successful running of media/awareness raising eventSpecialist operations as appropriate | W/c 3rd July 2023 | Oli Walker Nell Rodriquez |
| Engagement to Woking community in understanding ASB and tools used to tackle it:* Article in Woking magazine focusing on ASB
* Celebrating success in ASB
* Consult with residents where appropriate
* Attend Community events / engagement stands
 | Record of articles produced/disseminatedPromotion of ASB weekRetain any consultation undertakenRecord events attended designed to target identified issues | Throughout duration of action plan | Oli Walker Nell Rodriquez |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Crime*** **Knife Crime**
* **Domestic Violence**
* **Hate Crime**
* **Serious and Organised Crime (SOC)**
 | Knife Crime – specifically around young people carrying knives | 1-1 engagement with any identified young personIntelligence led targetingMonitor reoffending levels | Throughout duration of action plan | Nell Rodriquez |
| DA awareness weekWhite Ribbon campaign | Promotion of week and online campaignSocial media campaign and staff awareness sessions | June 2325th Nov – 10th Dec 2023 | Camilla Edmiston |
| Support Hate crime awareness week 8th-16th October 2023, including case study | Successfully run media and awareness raising of event | 8th-16th October 2023 | Nell Rodriquez Oli Walker |
| Support thecounty lines intensification weeks | Support the county delivery mechanism | Throughout duration of action plan | Surrey PoliceCounty Lines CoordinatorNational Crime Agency |
| Promote awareness of Child Exploitation and how to identify itEncouraging submission of partnership intelligence forms | Promote through CHaRMM / SOCJAG and record forms submitted | Throughout duration of action plan | Nell Rodriquez Camilla Edmiston |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Drugs and alcohol** | Support Surrey Substance Misuse Strategy | Support the county delivery mechanism | Throughout duration of action plan | Smart GroupWomen’s Support CentrePolice Checkpoint |
| Support current licensing initiatives | Support efforts to establish local Pubwatch | Throughout duration of action plan | Matt CobbLeslie Sumner |
| Continue with Test Purchasing operations locally | Record results of pre-planned operationsRespond to any intel around premises suspected of selling unlawfully | Throughout duration of action plan | Leslie Sumner |
| **Preventing Violent Extremism** | Awareness raising and information sharing | Promote through multi agency meetings.Support the county delivery mechanism | Throughout duration of action plan | Nell Rodriquez Camilla Edmiston |
| Monitoring for future training opportunities | Disseminate any national training packages to all staff | Throughout duration of action plan | Nell RodriquezCamilla Edmiston |
|  | Provide WBC response to the annual Counter Terrorism Local Profile  | Sharing any local data or insights with Counter Terrorism Policing South East | December 2023 | Camilla Edmiston |
| **Reducing Reoffending** | Scoping of partnership prevention visits of top offenders | Identify prolific offenders and visit with relevant organisations outside of Police | Throughout duration of action plan | Nell Rodriquez |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Promotion of the Women’s Support Centre | Promote through multi agency meetings and any suitable organised events | Throughout duration of action plan | Leanne Spiller  Camilla Edmiston |
| Utilise opportunities within Probation, such as the Community Payback scheme | Delivery of unpaid work requirements eg Spring Clean | Throughout duration of action plan | Peter Nicholls |